# Auburn University

# Department of Speech, Language, and Hearing Sciences

# 2025-2029 Strategic Plan

# Goal #1: SLHS Exceptional Student Experience

WE WILL:

## Provide SLHS undergraduates more opportunities to explore the programming of our department and connect with faculty.

### Year one (2025)

Offer in-person open house for prospective graduate students in AuD and SLP to learn more about the department and faculty

Hold 1-2 coffee chats for undergraduate students to meet and get to know faculty

### Year two (2026)

Initiate departmental orientation for undergraduates

### Year three (2027)

Survey undergraduate students regarding their needs and facilitators/barriers to connection with faculty.

## Provide SLHS undergraduates with quality instruction and mentoring to provide the necessary foundations for success in the undergraduate program and for graduate school.

### Year one (2025)

Hold brown bag discussion with CLA advisors regarding degree options and the graduate school application process

Pilot peer tutoring in SLHS 3410 Phonetics and SLHS 3550 Speech Science

Investigate the feasibility of a continuous improvement plan with AU Online for online courses

### Year two (2026)

Continue Peer tutoring in SLHS 3410 and SLHS 3550; Add SLHS 3400 A&P

### Year three (2027)

Continue peer tutoring in SLHS 3410 and SLHS 3550, and SLHS 3400; Add SLHS 3560 Neuroanatomy

## Provide SLHS graduate and undergraduate students with a curriculum that reflects current needs within the professions of speech-language pathology and audiology

### Year one (2025)

Initiate MS SLP Curriculum Revisions

Submit AuD Curriculum Revisions

### Year two (2026)

Initiate AuD Curriculum Revisions

### Year three (2027)

Conduct a self-assessment of the UG curriculum

## Initiate a Ph.D. program

### Year one (2025)

Pursue 1st faculty hire

Create space for additional needs associated with the PhD program

Recruit potential doctoral students for the PhD program

### Year two (2026)

Initiate 1st application cycle for the Ph.D. program

Initiate PhD Program (Fall 2026); Have 1-2 students enrolled in PhD program

Pursue 2nd faculty hire

### Year 3 (2027)

Have 2-3 students enrolled in PhD program

### Year 4 (2028)

Have 3-4 students enrolled in PhD program

### Year 5 (2029)

Have 4-5 students enrolled in the PhD program

# Goal #2: SLHS Impactful Research and Creative Scholarship

WE WILL:

## Improve quantity and quality of research and scholarship by building infrastructure

### Year one (2025)

The department will have a minimum of two external grant submissions per year

Identify all institutionally sponsored grant funding opportunities

Faculty will have an average of 1-2 publications per year in journals with a reported impact factor

### Year two (2026)

The department will have a minimum of three external grant submissions per year

The department will have a minimum of 2 internal grant submissions per year

Faculty will have an average of 2-3 publications per year in journals with a reported impact factor

### Years three through five (2027 - 2029)

Maintain 3 external grant submission with one being federal.

Faculty will have an average of 2-3 publications and an additional 1-2 submissions per year to journals with reported impact factors

## Increase national and international reputation through presentations at national and international conventions

### Year one (2025)

Obtain baseline data for current number of national and international presentations

### Year two (2026)

Maintain and expand the number of national and international presentations over the previous year

### Year three through five (2027-2029)

Secure external travel funding for national and international travel

Maintain the expanded number of national and international presentations

## Revise P&T Standards to be Commensurate with aspirational peers

### Year one (2025)

Form a committee to identify where we currently stand in the national reputation and review P&T standards from an aspirational university

Revise P&T standards and present to faculty for ratification.

### Year 2

Incorporate changes into offer letters for incoming faculty

### Year 3 (2027)

Implement new P&T standards

### Year 5 (2029)

Revisit P&T standard implementation to determine if adjustment is necessary

## Revise Tenure Track Annual Review Guidelines to be commensurate with P& T standards

### Year one (2025)

Form a committee to review merit processes by reviewing those of departments at the university with doctoral programs and aspirational programs in the discipline at peer institutions.

Operationally define a 2-2 workload

Update annual review process and workload guidelines.

Present revised academic merit processes for ratification

### Year two (2026)

Update policies and procedures to reflect new merit processes

### Year 3 (2027)

Apply new merit guidelines to the Faculty Annual Review

### Year 5 (2029)

Revisit FAR guidelines to determine if adjustments are necessary

## Develop a plan for space needs associated with increased faculty

### Year one (2025)

Executive committee meets to determine office and lab space for incoming 2025 hires

Consult with the dean on the possibility of space outside of the quadrant.

Develop a contingency plan based on the current space in the 1100 quadrant for office and lab needs associated with Ph.D. program hires

### Year two (2026)

Determine office and lab space for 2026 hire associated with Ph.D. program

Determine workspace for incoming Ph.D. students

### Year three (2027)

Determine office and lab space for 2027 hire associated with the Ph.D. Program

## Mentor Student Research

### Year one (2025)

Submit undergraduate research fellowships every year

Investigate funding opportunities for student research presentations at national/international conferences

An average of five theses every year

Goal of eighty percent of capstone projects submitted are accepted for publication/national presentation/proposal submission

### Years two through five (2025-2029)

Submit undergraduate research fellowships every year

An average of five theses every year

Goal of eighty percent of capstone projects submitted are accepted for publication/national presentation/proposal submission

# Goal #3: SLHS Commitment to Excellence and Innovation

WE WILL:

## Work to ensure that facilities meet or exceed academic and clinical needs

### Year one (2025)

Secure a new golf cart for the AUSHC

Finalize renovations with increased accessibility and features to benefit clients

### Year two (2026)

All faculty will have completed training required to use EASL classroom spaces

Assess how well current clinical spaces are meeting training and service provision needs

Investigate possibility of having integrated learning resources in the dedicated SLHS classroom

## Seek and secure opportunities for recognition of faculty, staff, and students

### Year one (2025)

The awards and nominations committee will operationalize a process for nominations

Identify all appropriate college and university level award opportunities

Identify at least two appropriate professional award opportunities

### Years one through five (2025-2028)

Nominate at least two faculty, staff or students for awards at the college or university level

Nominate at least one faculty member for an award at the professional level

## Continue to support employee development

### Years one through five (2025)

Hold a brown bag each Fall and Spring Semester to support faculty development

Provide funds for faculty travel to support CEUs

Annually assess faculty training needs (e.g., grant support, pedagogy, clinical development)

## Continuously improve processes

### Year one (2025)

Identify possible alternatives to EMR

Assess graduate admissions processes for needed revisions

Explore the possibility of a Clinic Director position

# Goal #4: SLHS Catalytic Engagement

WE WILL:

## Be a premier resource for the professions of speech language pathology and audiology

### Year one (2025)

Establish a CE committee

Complete CE application

### Year two (2026)

Plan and hold first CE opportunity for preceptors

### Years three through five

Plan and hold at least one CE opportunity

## Increase engagement with community

### Years one through five (2025)

Identify two new community partners for local presentations by community

Work with NSSLHA and SAA to identify community partners who would benefit from philanthropy events (e.g., REACH)

## Continue to grow our partnership with the Rural Health Initiative

### Year one (2025)

Increase SLP caseload by 1-2 clients

Increase hearing aid fittings by 1 per month

Identify 1 new partnership in the area

Reapply for the Alabama Relay hearing aid grant to include Chambers and Lee County

### Year 2 (2026)

Apply for extramural funding to acquire additional materials

Work with RHI to develop dedicated space for SLHS in Chambers County

### Year 3 (2027)

Increase SLP caseload by 2-3 clients

Increase hearing aid fittings by 2-3 per month

### Year 4 (2028)

Continue to expand SLP and audiology caseloads.

### Year 5 (2029)

Provide a full day of audiology and SLP services in Chambers County

## Maintain current collaborations across campus and add additional partnerships.

### Year one (2025)

Identify possible community facilities to provide speech and language services

Identify possible practicum placement opportunities

Explore partnerships with healthcare administration (e.g., internship in front office, guest lectures, student collaborative opportunities)

## Expand international collaboration opportunities

### Year one (2025)

Continue to market and recruit for current SLHS abroad opportunities (e.g., Global Perspectives in SLP and Guatemala AuD outreach)

### Year two (2026)

Form a committee to investigate the viability of virtual or in-person collaboration opportunities for students and/or faculty

# Goal # 5 Distinctively Auburn

WE WILL:

## Build Department Visibility Through Branding and Marketing Efforts

### Year one (2025)

Form marketing and branding committee to determine current methods and effectiveness

Identify new methods and sources of funding for marketing efforts

Identify areas of improvement in the department website

Place order for updated departmental items to be used at information fairs, outreach events, and recruitment events

Increase social media presence – investigate possibility of an intern from communication and journalism

Work with development to explore ways to connect with community stakeholders (alumni, clients)

### Year 2 (2026)

Develop a marketing plan for the AUSHC

Implement website redesign for graduate programs

Make plans based on what is learned on ways to connect

### Year 3 (2027)

Implement marketing plan

Implement website redesign for undergraduate program

Implement plan to connect with community stakeholders

## Establish a reciprocal relationship with alumni

### Year one (2025)

Plan clinic open house for a home game day

### Year 2 (2026)

Launch departmental newsletter

Hold one clinic open house per year

### Years 3 through 5 (2027-2029)

Publish a departmental newsletter in the beginning of Fall semester and the end of Spring semester